## My Home 99
Project Info Sheet_2215409 _My Home 99_Rev 5
Project Name | Myhome 99
Project Code | 2215409
Fabricator | Active Green Products
Project Bid Value | 180000000
Schueco Value WO/GST | 66407112.6301 |  | 10101.8 | With Coating & Without Wastage
Project Area In Sq.mt | a.Fenestration |  | 66407112.6301
| b.Façade |  | NA
Project Completion Date | 2028-04-01
Rate Agreed | Per Sft Without Wastage |  | 610.72
|  |  | Value | Qty | Sqm
System | 1 | Schüco AS SC 32 NI | 7893522 |  | 1012
| 2 | Schüco AS SC 39 NI (2.0) | 45481222 |  | 7339
| 3 | Schüco AW 40.NI | 5666029 |  | 670
|  | Schüco AWS/ADS 50.NI | 1516212 |  | 153
|  | Schüco AD 40 NI | 2116055 |  | 282
|  | Schüco AS43SC.NI | 3734070 | 26 | 644
Know Your Customer |  |  | 66407112.6301 | 26 | 10100
| a | End Customer |  | Myhome Construction
| b | Fabricator |  | Active Green Products
| c | Architect |  | Inhouse Architect
| d | Consultant |  | Aspect Façade Consultant
| e | PMC
Comercial
| a. | PO to Schueco | Yes | Recevied
| b. | Nalco | Applicable | 268 +/- 5%
| c. | Tolorance | Acceptable
| d. | Wastage | Without wastage | Wastage fabricator scope
| e. | Lots |  | 4 to 5 lots
| f. | Payment Terms (Client to Fabricator) |  | Refer Attached WORK/PURCHASE ORDER to fabricator
|  | Advance (Fabricator to Schueco) |  | 15 to 20% lot wise advance for booking
|  | Payment Terms (Fabricator to Schueco) |  | Utilization of existing CL or before dispach complete payment against the PI value
| g. | MOQ |  | Yes
| h. | Article Price Validity |  | 2027-04-01
Documents
| a. | WO From Client | Received | Active Green Products
| b. | PO From Fabricator | Received | Received
| c. | Final UOV | Approved | Received
| d. | Final PMS | Yes | Received
| e. | Tender Documents | Yes | Received
| f. | Technical Specification | Yes | Received
| g. | Wind loads | Yes | 2.35kPa, 2.65Kpa & 3Kpa
| h. | Material technical Data Sheet | Received | Submitted
| i. | MTC | Yes | Each Lot to be submit
Schueco Scope Engineering
| a. | Concept Proposal | Yes | Approved
| b. | Cadd Blocks | Yes | Received
| c. | Templates | Yes | NO
| d. | Production Drawing | Yes | Yet to receive
| e. | Shop Drawing | NO | Active Green Products
| f. | Shop drawing review | Yes | Schueco
| g. | B Drawings | NO | Yet to receive
| h. | V10 Drawings | NO | NA
| i. | V8 Drawings | NO | NA
| j. | Die Development | NO | NA
| k. | No Of New Dies | NO | NA
| l. | Production Documents | Yes | Schueco
Scope | a. | Powder Coating | Yes | Schueco Scope
| b. | Shade Approval | Yes | Refer Tender File
| c. | PC Coating Thickness |  | 60 to 120 Microns
| d. | Handle Shade | No | Black
| e. | Glass | Client Scope | Different Glass Tickness
| f. | Sealant Colour |  | Active Green Products
Material Procurement | a. | Long Lead Articles | Yes | Not Yet Done
| b. | No Of Lots | Yes | 4 to 5 lots
| c. | Lots requirement | Yes | 30-45 days Profile/50-55 days accessories
| d. | Material delivery timelines |  | 55-60 days
| e. | Schueco Flex Colour (Grey/Black) |  | Black
| f. | Orderlist Preperation | Yes | Schueco Scope
| g. | PI Generation | Yes | Schueco Scope
Mock-Up | a. | PMU | Yes | NA
|  | PMU Lab | Yes | NA
|  | PMU Testing System | N/A | NA
| b. | VMU | Yes | Ongoing
Project Warranties | a. | Schueco System Warranties | Yes | 10 Years
| b. | Hardware Warranty | Yes | 2 Years
| c. | Powder Coating Warranty | Yes | 15 Years
Service Audits | a. | System Fabrication Training | Yes | All System
| b. | System Installation Training | Yes | Custom Design System
| c. | Fabrication Audits | Yes | Every 15-20 Days
| d. | Installation Audits | Yes | Every 15-20 Days
Project Details |  | Tower 1 | 55 Floor
2 Flats / per Floor
Project Image 3D Redering
Project Construction Images | Tower 01